## Projects
Project | Start | End | Completion | Budget target, mln. | Budget actual, mln.
Baltimore | 2022-08-09 | 2023-08-09 | 53% | 450 | 240
Atlanta | 2023-01-01 | 2023-06-10 | 60% | 340 | 210
San Diego | 2022-08-15 | 2023-03-04 | 35% | 290 | 100
Austin | 2022-08-16 | 2023-12-23 | 12% | 190 | 10
Dallas | 2022-06-10 | 2023-05-10 | 34% | 410 | 170
Chicago | 2023-04-23 | 2023-10-23 | 90% | 700 | 810
Houston | 2022-08-09 | 2022-12-23 | 38% | 350 | 205
Miami | 2022-08-28 | 2023-09-01 | 89% | 550 | 500
Denver | 2023-02-14 | 2023-09-07 | 55% | 200 | 190
Portland | 2022-09-28 | 2023-07-12 | 12% | 210 | 32
Salt Lake City | 2022-09-28 | 2023-06-12 | 26% | 210 | 35
Phoenix | 2022-09-30 | 2023-01-01 | 14% | 210 | 25

## hierarchy
Project | Stage | Start | End | Completion
Baltimore | Project development | 2022-08-09 | 2022-09-12 | 100%
Baltimore | Project definition | 2022-09-12 | 2022-09-26 | 100%
Baltimore | Site preparation | 2022-09-26 | 2022-12-20 | 100%
Baltimore | Finish work | 2022-12-20 | 2023-04-01 | 100%
Baltimore | Site improvements | 2023-04-01 | 2023-07-01 | 100%
Baltimore | Facility commissioning | 2023-07-01 | 2023-08-09 | 53%
Atlanta | Project development | 2023-01-01 | 2023-03-01 | 100%
Atlanta | Project definition | 2023-03-01 | 2023-03-15 | 100%
Atlanta | Site preparation | 2023-03-15 | 2023-04-01 | 100%
Atlanta | Finish work | 2023-04-01 | 2023-06-01 | 100%
Atlanta | Site improvements | 2023-05-23 | 2023-06-10 | 60%
Atlanta | Facility commissioning | 2023-05-28 | 2023-06-10 | 12%
San Diego | Project development | 2022-08-15 | 2022-09-04 | 100%
San Diego | Project definition | 2022-08-22 | 2022-10-15 | 100%
San Diego | Site preparation | 2022-10-15 | 2023-01-16 | 100%
San Diego | Finish work | 2023-01-01 | 2023-02-01 | 35%
San Diego | Site improvements | 2022-12-24 | 2023-03-04 | 10%
San Diego | Facility commissioning | 2023-02-12 | 2023-03-04 | 0%
Austin | Project development | 2022-08-16 | 2022-09-12 | 100%
Austin | Project definition | 2022-09-12 | 2022-09-24 | 50%
Austin | Site preparation | 2022-09-24 | 2023-01-01 | 0%
Austin | Finish work | 2022-12-30 | 2023-04-30 | 0%
Austin | Site improvements | 2023-04-14 | 2023-06-26 | 0%
Austin | Facility commissioning | 2023-06-26 | 2023-12-23 | 0%

## Details
Project | Stage | Task | In charge | Status | Start | End | Completion
Baltimore | Project development | Building permission | J.Belly | Completed | 2022-08-09 | 2022-09-12 | 100%
Baltimore | Project development | Construction site design | G.James | Completed | 2022-08-12 | 2022-09-14 | 100%
Baltimore | Project development | Construction estimate | A.Lee | Completed | 2022-09-26 | 2022-12-20 | 100%
Baltimore | Project definition | Styling design conception | G.James | Completed | 2022-12-20 | 2023-04-01 | 100%
Baltimore | Project definition | Text documentation | B.Cooper | Completed | 2023-04-01 | 2023-07-01 | 100%
Baltimore | Site preparation | Area clearance | S.Sailor | Completed | 2023-04-01 | 2023-04-19 | 100%
Baltimore | Finish work | Electric work | J.Rush | Completed | 2023-05-09 | 2023-06-15 | 100%
Baltimore | Finish work | Engeneering works | A.Lee | Completed | 2023-05-15 | 2023-07-04 | 100%
Baltimore | Finish work | Panting works | P.Laider | Completed | 2023-06-28 | 2023-07-20 | 100%
Baltimore | Site improvements | Residenial landscaping | S.Camper | Completed | 2023-06-10 | 2023-06-22 | 100%
Baltimore | Facility commissioning | Delivery of keys | G.James | In progress | 2023-07-22 | 2023-08-09 | 53%
Austin | Project development | Building permission | H.Heiley | Completed | 2022-08-16 | 2022-09-12 | 100%
Austin | Project development | Master layout | A.Lee | Completed | 2022-08-22 | 2022-10-15 | 100%
Austin | Project development | Consolidating data | K.Tompson | Completed | 2022-08-15 | 2022-10-16 | 100%
Austin | Project definition | Styling design conception | S.Camper | In progress | 2022-09-12 | 2022-11-01 | 40%
Austin | Project definition | Text documentation | G.James | In progress | 2022-12-24 | 2023-03-04 | 35%
Austin | Site preparation | Area clearance | S.Sailor | Cancelled | 2023-02-12 | 2023-03-04 | 0%
Austin | Site preparation | Building envelope | H.Heiley | In progress | 2023-03-04 | 2023-04-12 | 10%
Austin | Finish work | Electric work | J.Belly | In progress | 2023-04-12 | 2023-06-24 | 34%
Austin | Finish work | Engeneering works | G.Kim | Suspended | 2023-06-24 | 2023-11-01 | 0%
Austin | Site improvements | Residenial landscaping | J.Rush | Suspended | 2023-09-30 | 2023-11-30 | 0%
Austin | Site improvements | Planting of trees and shrubs | R.Breiner | In progress | 2023-10-14 | 2023-11-26 | 0%
Austin | Facility commissioning | Signing of an act | J.Rush | Cancelled | 2023-12-20 | 2023-12-23 | 0%